## 04182025
Project Name | KPI | Description | Target | Current Status | Progress/Comments | Owner | Review Frequency
Digital Marketing Literacy (DML) | Outreach Engagement | Number of outreach interactions (e.g., in-person & social media views) | 75% engagement | 510 views, 12 interactions | Achieved 510 views online | Rymo Cortado | Weekly
Digital Marketing Literacy (DML) | Participant Follow-up | Percentage of participants who complete the sign-up process | 80% follow-up rate | 13 out of 16 completed interest forms | Majority of participants have filled forms | Rymo Cortado | Weekly
Digital Marketing Literacy (DML) | Recruitment | Number of participants recruited per session or outreach | 20 participants per event | 3 participants following up | Building relationships with schools for recruitment | Rymo Cortado | Weekly
Digital Marketing Literacy (DML) | Milestone Completion | Progress of digital marketing content creation (video courses) | 100% completion | Curriculum finalized | Video course materials finalized | Francisco Rullan | Monthly
Social Impact Program (SIP) | Session Attendance | Attendance rate for training sessions | 90% attendance | 100% attendance achieved | All sessions complete with full attendance | Javier Barrios | Weekly
Social Impact Program (SIP) | Alumni Network Engagement | Engagement with alumni network (social media, visits, etc.) | 100 engagements | 220 unique visitors | Increased pageviews, engagement on alumni network | Javier Barrios | Monthly
Social Impact Program (SIP) | Milestone Completion | Completion of public health and survey-related milestones | 100% completion | 4/4 tasks completed | Survey questions, digital tools completed | Javier Barrios | Monthly
Social Impact Program (SIP) | Event Preparation | Progress on event logistics, speaker recruitment, and materials | 80% preparation done | 90% attendance confirmation | Finalizing logistics for event | Javier Barrios | Weekly
I Am Community (IAC) | Curriculum Development | Percentage of curriculum finalized and approved | 100% curriculum completion | 80% curriculum ready | Meeting with schools to finalize | Rymo Cortado | Weekly
I Am Community (IAC) | Youth Engagement | Number of youth participating in IAC activities | 40 youth per session | 20 participants confirmed | Building relationships with schools for recruitment | Rymo Cortado | Bi-weekly
I Am Community (IAC) | Program Logistics | Number of logistical details confirmed (dates, locations) | 100% logistics confirmed | 90% confirmation | Scheduling campus visits | Rymo Cortado | Weekly
Qualitative Research (QR) | Youth Ambassador Recruitment | Number of ambassadors recruited for program | 10 youth ambassadors | 16 ambassadors recruited | Onboarding participants for program | Rymo Cortado | Weekly
Qualitative Research (QR) | Enrollment Completion | Percentage of enrolled participants who completed onboarding | 75% completion | 81% completion rate | Majority of participants have filled forms | Rymo Cortado | Weekly
Qualitative Research (QR) | Survey Completion | Completion of surveys by recruited participants | 100% survey completion | 75% completion rate | 12 interactions recorded | Rymo Cortado | Bi-weekly
City of Vallejo Youth SUD Prevention Project | Coordination of Drug Education Support Services | Percentage of communication milestones met with VCUSD | 100% communication achieved | Status TBD | Ongoing coordination | Francisco Rullan | Monthly
City of Vallejo Youth SUD Prevention Project | 24 Youth Group and School Classes | Number of workshops held per month (target: 24/year) | 2 workshops/month | Status TBD | Community outreach efforts | Francisco Rullan | Monthly
City of Vallejo Youth SUD Prevention Project | Site Clean-Ups | Number of clean-up events completed per month (target: 4-6) | 4-6 events/month | Status TBD | Event promotion ongoing | Francisco Rullan | Monthly
City of Vallejo Youth SUD Prevention Project | Advanced Peace Workshops | Number of workshops conducted for the Employment and Delinquency Program youth (target: 4 workshops/year) | 12 workshops/year | Status TBD | Event promotion ongoing | Francisco Rullan | Monthly
City of Vallejo Youth SUD Prevention Project | Referral Monitoring and Data Collection | Percentage of referrals monitored and data collected | 100% referral tracking | Status TBD | Monitoring data quality | Francisco Rullan | Bi-weekly
City of Vallejo Youth SUD Prevention Project | Community Engagement | Number of community partnerships and engagements formed | 5 new partnerships | Status TBD | Community partnerships forming | Francisco Rullan | Quarterly

## 04292025
Project Name | KPI | Description | Target | Current Status | Progress/Comments | Owner | Review Frequency
Digital Marketing Literacy (DML)
Digital Marketing Literacy (DML)
Digital Marketing Literacy (DML)
Digital Marketing Literacy (DML)
Social Impact Program (SIP)
Social Impact Program (SIP)
Social Impact Program (SIP)
Social Impact Program (SIP)
I Am Community (IAC)
I Am Community (IAC)
I Am Community (IAC)
Qualitative Research (QR)
Qualitative Research (QR)
Qualitative Research (QR)
City of Vallejo Youth SUD Prevention Project
City of Vallejo Youth SUD Prevention Project
City of Vallejo Youth SUD Prevention Project
City of Vallejo Youth SUD Prevention Project
City of Vallejo Youth SUD Prevention Project
City of Vallejo Youth SUD Prevention Project